## Report
Backend: | NodeJS,express | Employee Attendance System Web Application(Admin Panel)
Frontend: | ReactJS
Database: | Mysql
Sr.No | Action | Responsible | Priority | Status | Start Date | Planned Finish Date | Actual Finish Date | Notes
1 | admin signin and Signup (UI) | Vardhana Mane | Mid | completed | 2023-06-12 | 2023-06-12 | 2023-06-12
2 | Admin API (signin,signup,department(insert,edit,delete),employee(insert,edit,delete),Leave(insert,edit,delete) | vardhanaMane | MID | completed | 2023-06-13 | 2023-06-13 | 2023-06-13
3 | Frontend and backend Integration(signin,signup,delete and upload image) with admin panel | Vardhana Mane | MID | completed | 2023-06-14 | 2023-06-14 | 2023-06-15
4 | admin details view page (UI) | Vardhana Mane | MID | completed | 2023-06-15 | 2023-06-15 | 2023-06-15
5 | admin Dashboard | Vardhana Mane | MID | In progress | 2023-06-16 | 2023-06-20